## Sprint Tracker
Version	Phase	Sprint	Task	Guardrails	Implementation Scope	Deliverables	Definition of Done	Quality Gate
v0.1	Authoring Bootstrap (Phase A)	0.1-A	Sprint outcome — Parse and diagnose	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.1	Authoring Bootstrap (Phase A)	0.1-A	Engine: Implement lexer/tokenizer for indentation-aware blocks.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Implement lexer/tokenizer for indentation-aware blocks.	Implement lexer/tokenizer for indentation-aware blocks.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.1	Authoring Bootstrap (Phase A)	0.1-A	Engine: Implement parser support for `rule` blocks, `when` conditions, and `then` action lists (minimal subset).	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Implement parser support for `rule` blocks, `when` conditions, and `then` action lists (minimal subset).	Implement parser support for `rule` blocks, `when` conditions, and `then` action lists (minimal subset).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.1	Authoring Bootstrap (Phase A)	0.1-A	Tooling/DX: Add deterministic diagnostic format (file, line, column, code, message).	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Add deterministic diagnostic format (file, line, column, code, message).	Add deterministic diagnostic format (file, line, column, code, message).; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.1	Authoring Bootstrap (Phase A)	0.1-A	Tests/Correctness: Add parser golden tests (valid/invalid fixtures).	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Add parser golden tests (valid/invalid fixtures).	Add parser golden tests (valid/invalid fixtures).	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.1	Authoring Bootstrap (Phase A)	0.1-A	Docs: Write `docs/dsl_quickstart.md` (author + validate examples).	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Write `docs/dsl_quickstart.md` (author + validate examples).	Write `docs/dsl_quickstart.md` (author + validate examples).	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v0.1	Authoring Bootstrap (Phase A)	0.1-B	Sprint outcome — Ship samples + docs	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.1	Authoring Bootstrap (Phase A)	0.1-B	Product: Add `examples/equity_min_rules/` with 10 minimal rules and expected `validate` outputs.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Add `examples/equity_min_rules/` with 10 minimal rules and expected `validate` outputs.	Add `examples/equity_min_rules/` with 10 minimal rules and expected `validate` outputs.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v0.1	Authoring Bootstrap (Phase A)	0.1-B	Tooling/DX: Implement `sigmarule fmt` (minimal formatter / normalize indentation) *only if trivial*; otherwise defer.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Implement `sigmarule fmt` (minimal formatter / normalize indentation) *only if trivial*; otherwise defer.	Implement `sigmarule fmt` (minimal formatter / normalize indentation) *only if trivial*; otherwise defer.; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.1	Authoring Bootstrap (Phase A)	0.1-B	Tests/Correctness: Add CLI snapshot tests (stdout golden files).	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Add CLI snapshot tests (stdout golden files).	Add CLI snapshot tests (stdout golden files).	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.2	Typed Authoring (Phase A)	0.2-A	Sprint outcome — Type checker v1	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.2	Typed Authoring (Phase A)	0.2-A	Engine: Implement type model: primitives + `Price`, `Quantity`, `Percent`, `Timestamp`, `Duration`.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Implement type model: primitives + `Price`, `Quantity`, `Percent`, `Timestamp`, `Duration`.	Implement type model: primitives + `Price`, `Quantity`, `Percent`, `Timestamp`, `Duration`.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.2	Typed Authoring (Phase A)	0.2-A	Engine: Implement type checking for comparisons, boolean expressions, and action argument types.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Implement type checking for comparisons, boolean expressions, and action argument types.	Implement type checking for comparisons, boolean expressions, and action argument types.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.2	Typed Authoring (Phase A)	0.2-A	Tooling/DX: Improve error messages with “expected vs got” and source spans.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Improve error messages with “expected vs got” and source spans.	Improve error messages with “expected vs got” and source spans.; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.2	Typed Authoring (Phase A)	0.2-A	Tests/Correctness: Add type-check fixtures (good/bad).	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Add type-check fixtures (good/bad).	Add type-check fixtures (good/bad).	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.2	Typed Authoring (Phase A)	0.2-B	Sprint outcome — Profile compliance + forbidden constructs	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.2	Typed Authoring (Phase A)	0.2-B	Engine: Add AST validator for forbidden constructs: assignments, loops, function defs/calls outside whitelist.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Add AST validator for forbidden constructs: assignments, loops, function defs/calls outside whitelist.	Add AST validator for forbidden constructs: assignments, loops, function defs/calls outside whitelist.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.2	Typed Authoring (Phase A)	0.2-B	Engine: Implement “language profiles” validator: `signal` profile vs `intent`/`risk` (initially only `signal` allowed).	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Implement “language profiles” validator: `signal` profile vs `intent`/`risk` (initially only `signal` allowed).	Implement “language profiles” validator: `signal` profile vs `intent`/`risk` (initially only `signal` allowed).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.2	Typed Authoring (Phase A)	0.2-B	Tooling/DX: Add `sigmarule lint` with stable rule codes.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Add `sigmarule lint` with stable rule codes.	Add `sigmarule lint` with stable rule codes.; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.2	Typed Authoring (Phase A)	0.2-B	Docs: Author “Language Guardrails” page mapping back to Ch 2.6 and Ch 10.	Python-shaped but not Python; no loops/assignments/unrestricted functions; deterministic diagnostics	Author “Language Guardrails” page mapping back to Ch 2.6 and Ch 10.	Author “Language Guardrails” page mapping back to Ch 2.6 and Ch 10.	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-A	Sprint outcome — Deterministic evaluator + trace	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-A	Engine: Implement deterministic evaluation loop: event → context → rule matching → actions → decision outputs.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Implement deterministic evaluation loop: event → context → rule matching → actions → decision outputs.	Implement deterministic evaluation loop: event → context → rule matching → actions → decision outputs.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-A	Engine: Implement deterministic ordering rules (rule ordering + stable tie-breakers).	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Implement deterministic ordering rules (rule ordering + stable tie-breakers).	Implement deterministic ordering rules (rule ordering + stable tie-breakers).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-A	Engine: Implement trace record model: rule fired, predicate outcomes, reason codes.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Implement trace record model: rule fired, predicate outcomes, reason codes.	Implement trace record model: rule fired, predicate outcomes, reason codes.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-A	Tests/Correctness: Add golden trace tests on small bar series.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Add golden trace tests on small bar series.	Add golden trace tests on small bar series.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-B	Sprint outcome — CLI run + JSON output	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-B	Product: Implement `sigmarule run --input bars.csv --rules path/` producing `decisions.jsonl`.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Implement `sigmarule run --input bars.csv --rules path/` producing `decisions.jsonl`.	Implement `sigmarule run --input bars.csv --rules path/` producing `decisions.jsonl`.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-B	Tooling/DX: Add `sigmarule explain --decision-id ...` to print a single decision’s trace (basic).	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Add `sigmarule explain --decision-id ...` to print a single decision’s trace (basic).	Add `sigmarule explain --decision-id ...` to print a single decision’s trace (basic).; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.3	Deterministic Evaluation (Equity) (Phase B)	0.3-B	Tests/Correctness: Add end-to-end fixtures: input CSV → expected JSON outputs.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Add end-to-end fixtures: input CSV → expected JSON outputs.	Add end-to-end fixtures: input CSV → expected JSON outputs.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-A	Sprint outcome — Event log + replay	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-A	Engine: Implement event log format (inputs + version pins + config) and deterministic replay loader.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Implement event log format (inputs + version pins + config) and deterministic replay loader.	Implement event log format (inputs + version pins + config) and deterministic replay loader.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-A	Product: Implement `sigmarule replay --log run.log` producing identical decisions.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Implement `sigmarule replay --log run.log` producing identical decisions.	Implement `sigmarule replay --log run.log` producing identical decisions.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-A	Tests/Correctness: Add “replay must match” golden tests.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Add “replay must match” golden tests.	Add “replay must match” golden tests.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-B	Sprint outcome — Explain UX + golden suite	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-B	Tooling/DX: Implement `sigmarule diff` to compare two runs (counts + first divergence) deterministically.	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Implement `sigmarule diff` to compare two runs (counts + first divergence) deterministically.	Implement `sigmarule diff` to compare two runs (counts + first divergence) deterministically.; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-B	Docs: Add “Debugging determinism” page (why/how to use replay + diff).	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Add “Debugging determinism” page (why/how to use replay + diff).	Add “Debugging determinism” page (why/how to use replay + diff).	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v0.4	MVP: Equity Rule Runner (Phase B)	0.4-B	Tests/Correctness: Expand golden suite across OS/timezone invariants (timestamp handling policy).	Deterministic evaluation order; explainability trace; replay-ready semantics; no broker execution in DSL	Expand golden suite across OS/timezone invariants (timestamp handling policy).	Expand golden suite across OS/timezone invariants (timestamp handling policy).	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.5	Indicators + Feature Registry (Phase C)	0.5-A	Sprint outcome — Indicator registry + caching	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.5	Indicators + Feature Registry (Phase C)	0.5-A	Engine: Implement indicator registry with explicit version pinning.	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs	Implement indicator registry with explicit version pinning.	Implement indicator registry with explicit version pinning.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.5	Indicators + Feature Registry (Phase C)	0.5-A	Engine: Implement deterministic windows and bar alignment semantics (fixed policy).	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs	Implement deterministic windows and bar alignment semantics (fixed policy).	Implement deterministic windows and bar alignment semantics (fixed policy).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.5	Indicators + Feature Registry (Phase C)	0.5-A	Tests/Correctness: Golden numeric tests for EMA/RSI/ATR/VWAP with fixed rounding.	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs	Golden numeric tests for EMA/RSI/ATR/VWAP with fixed rounding.	Golden numeric tests for EMA/RSI/ATR/VWAP with fixed rounding.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.5	Indicators + Feature Registry (Phase C)	0.5-B	Sprint outcome — Indicator-based sample strategies	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.5	Indicators + Feature Registry (Phase C)	0.5-B	Product: Add `examples/equity_indicator_rules/` with 10 rules and expected results on sample datasets.	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs	Add `examples/equity_indicator_rules/` with 10 rules and expected results on sample datasets.	Add `examples/equity_indicator_rules/` with 10 rules and expected results on sample datasets.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v0.5	Indicators + Feature Registry (Phase C)	0.5-B	Docs: Add “Indicator cookbook” pages with inputs/outputs.	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs	Add “Indicator cookbook” pages with inputs/outputs.	Add “Indicator cookbook” pages with inputs/outputs.	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v0.5	Indicators + Feature Registry (Phase C)	0.5-B	Tooling/DX: Add `sigmarule profile` summary (what indicators/actions a pack uses).	Deterministic indicators only; version pinning; fixed rounding/windows; reproducible outputs	Add `sigmarule profile` summary (what indicators/actions a pack uses).	Add `sigmarule profile` summary (what indicators/actions a pack uses).; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.6	Library + Packaging (Phase D)	0.6-A	Sprint outcome — Imports + module layout	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.6	Library + Packaging (Phase D)	0.6-A	Engine: Implement module/import resolution rules (no dynamic imports; deterministic load order).	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes	Implement module/import resolution rules (no dynamic imports; deterministic load order).	Implement module/import resolution rules (no dynamic imports; deterministic load order).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.6	Library + Packaging (Phase D)	0.6-A	Engine: Add dependency graph validation + cycle detection.	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes	Add dependency graph validation + cycle detection.	Add dependency graph validation + cycle detection.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v0.6	Library + Packaging (Phase D)	0.6-A	Tests/Correctness: Fixtures for import resolution and cycle errors.	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes	Fixtures for import resolution and cycle errors.	Fixtures for import resolution and cycle errors.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v0.6	Library + Packaging (Phase D)	0.6-B	Sprint outcome — Rule pack packaging	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v0.6	Library + Packaging (Phase D)	0.6-B	Product: Implement pack manifest: name, version, compatibility, hashes.	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes	Implement pack manifest: name, version, compatibility, hashes.	Implement pack manifest: name, version, compatibility, hashes.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v0.6	Library + Packaging (Phase D)	0.6-B	Tooling/DX: Implement `sigmarule pack` and `sigmarule validate --pack file`.	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes	Implement `sigmarule pack` and `sigmarule validate --pack file`.	Implement `sigmarule pack` and `sigmarule validate --pack file`.; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v0.6	Library + Packaging (Phase D)	0.6-B	Docs: Add “Rule library model” page aligned to Ch 23.	Deterministic imports; no dynamic imports; compatibility metadata; reproducible pack hashes	Add “Rule library model” page aligned to Ch 23.	Add “Rule library model” page aligned to Ch 23.	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v1.0	Stable Equity Product (Phase E)	1.0-A	Sprint outcome — Signal/Intent/Risk profiles	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.0	Stable Equity Product (Phase E)	1.0-A	Engine: Implement profile-specific allowed verbs and outputs.	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Implement profile-specific allowed verbs and outputs.	Implement profile-specific allowed verbs and outputs.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.0	Stable Equity Product (Phase E)	1.0-A	Engine: Implement stable decision schema (signals/intents/constraints + trace).	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Implement stable decision schema (signals/intents/constraints + trace).	Implement stable decision schema (signals/intents/constraints + trace).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.0	Stable Equity Product (Phase E)	1.0-A	Tests/Correctness: Golden schemas + backward-compat checks for outputs.	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Golden schemas + backward-compat checks for outputs.	Golden schemas + backward-compat checks for outputs.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v1.0	Stable Equity Product (Phase E)	1.0-B	Sprint outcome — Risk constraints v1	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.0	Stable Equity Product (Phase E)	1.0-B	Engine: Implement risk rule evaluation as a separate phase that can block decisions (fail-closed).	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Implement risk rule evaluation as a separate phase that can block decisions (fail-closed).	Implement risk rule evaluation as a separate phase that can block decisions (fail-closed).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.0	Stable Equity Product (Phase E)	1.0-B	Product: Add `examples/risk_rules/` showing blocked trades and reasons.	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Add `examples/risk_rules/` showing blocked trades and reasons.	Add `examples/risk_rules/` showing blocked trades and reasons.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v1.0	Stable Equity Product (Phase E)	1.0-B	Tests/Correctness: Golden tests proving risk blocks are deterministic and replayable.	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Golden tests proving risk blocks are deterministic and replayable.	Golden tests proving risk blocks are deterministic and replayable.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v1.0	Stable Equity Product (Phase E)	1.0-C	Sprint outcome — Reports + UX polish	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.0	Stable Equity Product (Phase E)	1.0-C	Product: Implement `sigmarule report` (aggregate outcomes per rule/symbol/day).	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Implement `sigmarule report` (aggregate outcomes per rule/symbol/day).	Implement `sigmarule report` (aggregate outcomes per rule/symbol/day).	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v1.0	Stable Equity Product (Phase E)	1.0-C	Tooling/DX: Improve `explain` formatting: “why did/didn’t it fire?” outputs.	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Improve `explain` formatting: “why did/didn’t it fire?” outputs.	Improve `explain` formatting: “why did/didn’t it fire?” outputs.; stable CLI output	Command/output format stable; snapshot tests updated; deterministic across reruns	Snapshot tests stable; deterministic reruns
v1.0	Stable Equity Product (Phase E)	1.0-C	Docs: Add “Equity product quickstart” and “FAQ”.	Signal/intent/risk separation; fail-closed risk constraints; stable schemas; no broker execution in DSL	Add “Equity product quickstart” and “FAQ”.	Add “Equity product quickstart” and “FAQ”.	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v1.1	Options Contract Context (Phase F)	1.1-A	Sprint outcome — Option instrument model + types	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.1	Options Contract Context (Phase F)	1.1-A	Engine: Add option contract types, validation, and canonical identifiers.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add option contract types, validation, and canonical identifiers.	Add option contract types, validation, and canonical identifiers.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.1	Options Contract Context (Phase F)	1.1-A	Engine: Extend data model to include option snapshots (quotes/greeks inputs).	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Extend data model to include option snapshots (quotes/greeks inputs).	Extend data model to include option snapshots (quotes/greeks inputs).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.1	Options Contract Context (Phase F)	1.1-A	Tests/Correctness: Fixtures for expiry/strike validation and parsing.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Fixtures for expiry/strike validation and parsing.	Fixtures for expiry/strike validation and parsing.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v1.1	Options Contract Context (Phase F)	1.1-B	Sprint outcome — Option context binding	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.1	Options Contract Context (Phase F)	1.1-B	Engine: Implement `option` context binding rules and deterministic context selection.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Implement `option` context binding rules and deterministic context selection.	Implement `option` context binding rules and deterministic context selection.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.1	Options Contract Context (Phase F)	1.1-B	Product: Implement `sigmarule run --input options.csv` mode (or multi-input bundle).	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Implement `sigmarule run --input options.csv` mode (or multi-input bundle).	Implement `sigmarule run --input options.csv` mode (or multi-input bundle).	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v1.1	Options Contract Context (Phase F)	1.1-B	Docs: Add “Option context rules” tutorial.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add “Option context rules” tutorial.	Add “Option context rules” tutorial.	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v1.1	Options Contract Context (Phase F)	1.1-C	Sprint outcome — Selection helpers + examples	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.1	Options Contract Context (Phase F)	1.1-C	Engine: Add deterministic strike/expiry selection primitives (ATM/OTM, delta-based selection when available).	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add deterministic strike/expiry selection primitives (ATM/OTM, delta-based selection when available).	Add deterministic strike/expiry selection primitives (ATM/OTM, delta-based selection when available).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.1	Options Contract Context (Phase F)	1.1-C	Product: Add `examples/options_contract_rules/` with expected outputs.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add `examples/options_contract_rules/` with expected outputs.	Add `examples/options_contract_rules/` with expected outputs.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v1.1	Options Contract Context (Phase F)	1.1-C	Tests/Correctness: Golden tests for selection behavior.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Golden tests for selection behavior.	Golden tests for selection behavior.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v1.2	Option Chain Context (Phase F)	1.2-A	Sprint outcome — Chain schema + snapshot semantics	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.2	Option Chain Context (Phase F)	1.2-A	Engine: Implement chain snapshot schema and atomic retrieval semantics.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Implement chain snapshot schema and atomic retrieval semantics.	Implement chain snapshot schema and atomic retrieval semantics.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.2	Option Chain Context (Phase F)	1.2-A	Engine: Add staleness/quality guards as first-class predicates.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add staleness/quality guards as first-class predicates.	Add staleness/quality guards as first-class predicates.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.2	Option Chain Context (Phase F)	1.2-A	Tests/Correctness: Fixtures for incomplete chain handling and deterministic “unknown” outcomes (per policy).	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Fixtures for incomplete chain handling and deterministic “unknown” outcomes (per policy).	Fixtures for incomplete chain handling and deterministic “unknown” outcomes (per policy).	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v1.2	Option Chain Context (Phase F)	1.2-B	Sprint outcome — Derived chain metrics v1	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.2	Option Chain Context (Phase F)	1.2-B	Engine: Implement derived chain metrics functions with deterministic rounding.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Implement derived chain metrics functions with deterministic rounding.	Implement derived chain metrics functions with deterministic rounding.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v1.2	Option Chain Context (Phase F)	1.2-B	Product: Add chain analytics examples and expected outputs.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add chain analytics examples and expected outputs.	Add chain analytics examples and expected outputs.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v1.2	Option Chain Context (Phase F)	1.2-B	Tests/Correctness: Golden numeric tests for PCR/OI change/skew computations.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Golden numeric tests for PCR/OI change/skew computations.	Golden numeric tests for PCR/OI change/skew computations.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v1.2	Option Chain Context (Phase F)	1.2-C	Sprint outcome — Chain-driven worked examples	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v1.2	Option Chain Context (Phase F)	1.2-C	Product: Add chain-driven examples aligned to Ch 27.4 with deterministic outputs.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add chain-driven examples aligned to Ch 27.4 with deterministic outputs.	Add chain-driven examples aligned to Ch 27.4 with deterministic outputs.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v1.2	Option Chain Context (Phase F)	1.2-C	Docs: Add “Chain context cookbook”.	Deterministic option/chain contexts; atomic snapshots; staleness/quality guards; fixed rounding	Add “Chain context cookbook”.	Add “Chain context cookbook”.	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-A	Sprint outcome — Intent verbs v1	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-A	Engine: Implement intent actions as verbs with typed signatures and idempotency rules.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Implement intent actions as verbs with typed signatures and idempotency rules.	Implement intent actions as verbs with typed signatures and idempotency rules.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-A	Engine: Implement conflict resolution policy for multiple intents (deterministic tie-breakers).	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Implement conflict resolution policy for multiple intents (deterministic tie-breakers).	Implement conflict resolution policy for multiple intents (deterministic tie-breakers).; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-A	Tests/Correctness: Golden tests on intent conflict scenarios.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Golden tests on intent conflict scenarios.	Golden tests on intent conflict scenarios.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-B	Sprint outcome — Execution planning IR	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-B	Engine: Implement plan IR schema (entry/exit/size primitives) and deterministic plan generation.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Implement plan IR schema (entry/exit/size primitives) and deterministic plan generation.	Implement plan IR schema (entry/exit/size primitives) and deterministic plan generation.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-B	Product: `sigmarule plan` command outputs plan JSON for downstream adapters.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	`sigmarule plan` command outputs plan JSON for downstream adapters.	`sigmarule plan` command outputs plan JSON for downstream adapters.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-B	Tests/Correctness: Golden plan outputs for sample intents.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Golden plan outputs for sample intents.	Golden plan outputs for sample intents.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-C	Sprint outcome — Risk enforcement integrated	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-C	Engine: Integrate risk evaluation across signals→intents→plans; fail-closed defaults.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Integrate risk evaluation across signals→intents→plans; fail-closed defaults.	Integrate risk evaluation across signals→intents→plans; fail-closed defaults.; integrated into compiler/runtime	Implemented with deterministic behavior; unit/golden tests pass; no forbidden constructs introduced	Unit tests + goldens green; deterministic properties preserved
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-C	Product: `sigmarule plan --with-risk` outputs allowed/blocked plans with reasons.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	`sigmarule plan --with-risk` outputs allowed/blocked plans with reasons.	`sigmarule plan --with-risk` outputs allowed/blocked plans with reasons.	Feature works on sample packs/datasets; outputs match expected JSON/goldens	E2E fixtures pass; output schema validated; goldens stable
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-C	Tests/Correctness: Parity tests: same inputs + same outputs across replay.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Parity tests: same inputs + same outputs across replay.	Parity tests: same inputs + same outputs across replay.	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-D	Sprint outcome — Parity harness + contracts	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk			CLI works end-to-end on fixtures; deterministic reruns match; docs/examples updated	E2E fixtures + golden outputs stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-D	Tests/Correctness: Implement parity harness for backtest vs replay vs simulated-live modes (Ch 19).	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Implement parity harness for backtest vs replay vs simulated-live modes (Ch 19).	Implement parity harness for backtest vs replay vs simulated-live modes (Ch 19).	Fixtures + expected outputs added; tests pass on clean run; reruns produce identical outputs	Golden tests stable; test suite green
v2.0	Intent→Plan→Risk Platform (Phase G)	2.0-D	Docs: Document adapter contracts (Ch 25) and integration guidance.	Intent→plan→risk separation; deterministic conflict resolution; broker-agnostic plan IR only; fail-closed risk	Document adapter contracts (Ch 25) and integration guidance.	Document adapter contracts (Ch 25) and integration guidance.	Doc page added/updated; examples validated against current CLI	Docs examples verified via CLI on fixtures

## Version Summary
Version	Goal	User-visible capability	Major framework work	Risks retired	Notes
v0.1	“Validate rule files”	`validate` CLI with deterministic diagnostics on a small DSL subset	Lexer/parser skeleton + AST + diagnostics	Can parse safely without Python escape hatches	CLI: `validate`; Docs/examples: minimal rules + quickstart; Correctness: parser golden tests
v0.2	“Typed rules”	Type errors + profile checks; sample rule pack compiles	Type system + validators for forbidden constructs	Prevents unsafe/ambiguous authoring	CLI: `validate`, `lint`; Docs/examples: typed rule pack examples; Correctness: type-check fixtures
v0.3	“Run rules on bars”	`run` on OHLCV bars → signals + trace	Deterministic evaluator + trace model	Semantics are executable and explainable	CLI: `run`, basic `explain`; Docs/examples: equity bar runner examples; Correctness: golden traces
v0.4	“Replayable equity screener”	`run` + `explain` + `replay` on historical CSV with stable outputs	Event log + replay + golden tests	Deterministic replay parity starts	CLI: `replay`, `diff`, improved `explain`; Docs/examples: MVP tutorial + replay guide; Correctness: replay equivalence tests; Recommended MVP target in plan
v0.5	“Real indicators, still deterministic”	Built-in indicators (EMA/RSI/ATR/VWAP) used in rules	Indicator registry + caching/version pinning	Indicator correctness + reproducibility	CLI: indicator support in `run`; Docs/examples: indicator cookbook + realistic rules; Correctness: golden numeric tests
v0.6	“Reusable rule packs”	`pack`/`import` rules; semantic versioning; sample library	Module/import rules + pack metadata	Reuse, governance foundations	CLI: `pack`, deterministic `import`; Docs/examples: reusable library starter pack; Correctness: pack hash verification
v1.0	“Credible first product”	Equity screeners + intent-style outputs + risk constraints + reports	Rule profiles (signal/intent/risk) + stable CLI UX	First “platform-ready” core	CLI: `report`, stable schema; Docs/examples: equity product guide + FAQ; Correctness: schema compat tests
v1.1	“Option-aware rules”	`option` context: contract selection + greeks inputs (computed/pluggable)	Option instrument model + type extensions	Options correctness baseline	CLI: options input mode; Docs/examples: option context tutorials; Correctness: selection golden tests
v1.2	“Chain snapshots + analytics”	`chain` context queries + basic derived metrics; deterministic chain snapshot semantics	Chain schema + snapshot atomicity + feature ops	Chain determinism + staleness handling	CLI: chain input mode; Docs/examples: chain cookbook + worked examples; Correctness: chain determinism fixtures
v2.0	“Full separation realized”	Intent verbs + execution plan generation + strict risk enforcement + backtest parity suite	Plan IR + conflict resolution + parity harness	Integration-ready deterministic outputs	CLI: `plan` (+ risk); Docs/examples: integration guide (adapter contracts); Correctness: parity harness suite

## Phase Overview
Phase	Intent	Key chapters/docs mapped	Major risks retired	Notes
Phase A — Authoring + Validation (v0.1–v0.2)	Make the language safely authorable: parseable, typed, and impossible to misuse as Python.	Ch 10–12, Ch 14, Ch 21.2–21.4, Appendices A/B/E.	grammar ambiguity, unsafe constructs, unclear diagnostics.	Source: Project plan (Phase Breakdown)
Phase B — Deterministic Evaluation + Explainability (v0.3–v0.4)	Make rules executable with deterministic ordering, traces, and replay.	Ch 13–14, Ch 6, Ch 21.6, Ch 19.5.	“it runs but we can’t explain it”, nondeterministic results, inability to debug/verify.	Source: Project plan (Phase Breakdown)
Phase C — Indicators + Data Model Hardening (v0.5)	Add deterministic indicator registry and stable feature computation.	Ch 7, Ch 16, Appendix D/F.	indicator drift, inconsistent computations, missing data policies.	Source: Project plan (Phase Breakdown)
Phase D — Library Reuse + Governance (v0.6)	Make rule packs reusable, versioned, and importable.	Ch 11.7, Ch 23, Ch 25.4.	unmanageable rule sprawl, lack of upgrade discipline.	Source: Project plan (Phase Breakdown)
Phase E — Equity Productization (v1.0)	Deliver a stable equity rules product slice with risk constraints and reporting.	Ch 4, Ch 18, Ch 21, Ch 27.1, Ch 24.4 (observability basics).	product cohesion; “works in demos but not in usage”.	Source: Project plan (Phase Breakdown)
Phase F — Options + Chain Productization (v1.1–v1.2)	Add option contract context, then chain context, with deterministic semantics.	Ch 8, Ch 14.2, Ch 16.3–16.4, Ch 3.4–3.6.	chain staleness/atomicity; strike/expiry selection correctness.	Source: Project plan (Phase Breakdown)
Phase G — Intent→Plan→Risk Platform Readiness (v2.0)	Realize full separation of intent, planning, and risk enforcement with parity tests.	Ch 15, Ch 17–19, Ch 25, Ch 6.	unsafe execution coupling; inability to integrate into larger systems.	Source: Project plan (Phase Breakdown)